## Cover
AIO REGRESSION TEST CASES
Version:	1.6
Issue date:	5/May/2011
Project Suite:
Project Name:	WCM 1.2.x
Total Cases:	73
Test Status:	Passed: Test is OK / Blocked: Could not run the test (another bug is blocking) / Failed: Test failed, a bug is entered on it (please add the bug ID) / N/A: Test is not possible to run on this version

Record of change:
Effective Date	Version	Change description	Originator	Reviewer/ / Approver	Reference
04/Oct/10	1.0	AIO split to products	minh.nguyen
20/Oct/10	1.1	ALL-411 / CCP-496	minh.nguyen
	1.2	Missing: (technique) / - ECM-5458 / - Portal-3755 / - CS-4197 / - CS-4426 / - KS-2610 / - CS-4412 / - JCR-1411 / - WCM-2859 / - KS-2399 / - JCR-1401 / - Portal- 3814 / - WCM-2796 / - CCP-411 / - WCM-2815 / WCM-2857 (1.6.8) / WCM-2933 : required to hide the admin bar for 1 group but infact it was hidden for any group except web-contributor because of WCM-2601 / WCM-2947: won't fix / WCM-2922 / WCM-2961: bug found in AIO 1.6.1 from 1.6.6 the position of portlet are changed → can not reproduce / WCM-2993: Errors when importing CSS files in fckeditor -> releated to technical / - WCM-2928: won't fix / - WCM-2993 / - WCM-2963 (duplicate WCM-2962)
29/Nov/2010	1.3	Remove: / - CCP-483 (Do not allow to add document with name contain special characters)	an_Nguyen
5/Apr/2011	1.4	Add 2 first tests for AIO 1.6.9	minh.nguyen
27/Apr/2011	1.5	Add: / - WCM-2959 CCP-711 / - WCM-2962 CCP-711 / - WCM-2997 CCP-884	minh.nguyen
5/May/2011	1.6	Move WCM-2948 from Bugs_1.6.8 to 1.6.9	minh.nguyen

## Check_List
Check List / Based on Product built version:	Check List / Based on Product built version:	Check List / Based on Product built version:	Check List / Based on Product built version:	Check List / Based on Product built version:
Id	Main cases	Priority	Selenium	Table of record
Bugs on version 1.6.5
REG_AIO165_WCM_001	Can not download an uploaded document in PCV portlet	High		Total of High	0
REG_AIO165_WCM_002	Check if the content edition is considered after publication	High		Total of Medium	0
REG_AIO165_WCM_003	Cache & Categories with publication errors	High		Total of Low	0
REG_AIO165_WCM_004	Check if Newsletter mail's validator allows a multiple domain names in address mail	High
REG_AIO165_WCM_005	Check when publish content after image resize with Shift button pressed	High
REG_AIO165_WCM_006	Label categories are not traduced in clv edition	High
REG_AIO165_WCM_007	Check viewing localised content	High
REG_AIO165_WCM_008	Check translation of results' number after search	Low
REG_AIO165_WCM_009	Search result - wrong traduction when there's no result	Low
REG_AIO165_WCM_010	Check translation of label in the “Form Generator” portlet	Low
REG_AIO165_WCM_011	Mistakes in french internationalization	High
REG_AIO165_WCM_012	Check Sorting Mechanism	High
REG_AIO165_WCM_013	Check encoding when display Taxonomy in the CLV categories	High
REG_AIO165_WCM_014	Check showing webcontent by category (presentation portlet)	High
REG_AIO165_WCM_015	Check Manage taxonomy	High
REG_AIO165_WCM_016	Error while setting a page with PCLV portlet	High
REG_AIO165_WCM_017	Check Problem in downloading binary from PCLV	High
REG_AIO165_WCM_018	Check Problem with "Add a site page link " on FCKEDITOR	Low
REG_AIO165_WCM_019	Check play a media file that was published into a page	Low
REG_AIO165_WCM_020	Check listing content to be displayed in SCV when switch the filter condition	Low
REG_AIO165_WCM_021	Check display a link in a content	High
REG_AIO165_WCM_022	Check when select content from search result to view in CLV	High
REG_AIO165_WCM_023	Inversion of content's list in CLV at every validation	High
REG_AIO165_WCM_024	Changes in FCC action's parameters are not taken in consideration	High
REG_AIO165_WCM_025	Searched texts in search results are not highlighted
Bugs on version 1.6.6
REG_AIO166_WCM_001	A problem with clv when browsing directories with special characters (using IE7)	Low
REG_AIO166_WCM_002	Problem with displaying documents with name containing illegal JCR characters in PCLV	High
REG_AIO166_WCM_003	Can not order content in CLV manual browse	High
REG_AIO166_WCM_004	Search's results in FO: Results are not displayed when them number exceeds 250	High
REG_AIO166_WCM_005	Labels are not internationalized in WCMInsertContent functionality	High
REG_AIO166_WCM_006	Translation of links next and previous in WCM search (FO)	Low
REG_AIO166_WCM_007	Problem with FCK editor's insert link to a site page plugin	Low
REG_AIO166_WCM_008	Error when moving document containing illegal jcr characters	Low
REG_AIO166_WCM_009	the subnodes of nodes that don't have page reference are not shown in the navigation of the WCM site admin toolbar	High
REG_AIO166_WCM_010	Impossible to download a binary file with name containing an illegal jcr char (using the right popup menu)	Low
REG_AIO166_WCM_011	A problem with WCMInsertContent when browsing directories with special characters	High
REG_AIO166_WCM_012	Search does not ignore accented characters	High
REG_AIO166_WCM_013	Container can't be removed after being inserted in the page	Low
REG_AIO166_WCM_014	Broken design with empty CLV in manual mode	High
REG_AIO166_WCM_015	Show error message when trying to add new category in Newsletter Manager	High
REG_AIO166_WCM_016	Problem for displaying documents with names containing illegal JCR characters using nt:file view	High
REG_AIO166_WCM_017	Content selector does not work on IE7	Low
REG_AIO166_WCM_018	Portlet Category Navigation	High
REG_AIO166_WCM_019	Download a binary file with name containing an illegal jcr char (using the right popup menu)	High
Bugs on version 1.6.8
REG_AIO168_WCM_001	Portlet Category Navigation	High
REG_AIO168_WCM_002	Error while setting a page with PCLV portlet	High
REG_AIO168_WCM_003	Link still be referenced after being inserted	High
REG_AIO168_WCM_004	Duplicated portlet ID: Content List, Category Navigation, Category Content, Content by URL	High
REG_AIO168_WCM_005	Newsletter Wrong text of changing "Subscribe" in French	High
REG_AIO168_WCM_006	No attribute "target" in "ACME Overview" when checking with W3C	High
REG_AIO168_WCM_007	Impossible selection to insert contents into a text content	High
REG_AIO168_WCM_008	FCKEditor: Exception when creating page link after adding new page for the user navigation	High
REG_AIO168_WCM_009	CLV manual search content: Error when previewing content with image loaded from JCR	High
REG_AIO168_WCM_010	Add page wizards: Some labels are not translated in French	High
REG_AIO168_WCM_011	The selection of repository brings up some content	High
REG_AIO168_WCM_012	Impossible to select an invisible page when creating a portal page link into a text (FCK Editor)	High
REG_AIO168_WCM_013	Error in displaying .rtf file	High
REG_AIO168_WCM_014	Check showing quick edit icon on portlet in porlet mode	High
Bugs on version 1.6.9
REG_AIO169_WCM_001	Links are displayed not underlined when visited	High

## Bugs_v1_6_5
	TEST CASES					Passed	Passed	0	0	0	0
				Failed	Failed	0	0	0	0
	Function List:	Bugs on WCM 1.2.x for regression test					Blocked	Blocked	0	0	0	0
	Total Main Cases:	23					Untested	Untested	0	0	0	0
				N/A	N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
001	REG_AIO165_WCM_001	001	REG_AIO165_WCM_001	Can not download an uploaded document in PCV portlet	Step 1: Upload file	- Go to Site Explorer, ACME drive / - Upload a file (pdf for example) in a category	Upload file successfully	High	WCM-2157, SST-186, CCP-184	Upload a file (pdf for example) in a category
	REG_AIO165_WCM_001	001	REG_AIO165_WCM_001	Can not download an uploaded document in PCV portlet	Step 2: View uploaded file in News page	- Choose News page on ACME site / - Select category to view the uploaded file before / - Click to open the previously uploaded document / - Click Download this file link	Download file successfully	High	WCM-2157, SST-186, CCP-184
002	REG_AIO165_WCM_002	001	REG_AIO165_WCM_002	Check if the content edition is considered after publication	Step 1: Create a free layout web content	- Login by admin / - Go to Site Explorer → Site Administration / - Select 1 node & click Add document / - Select Free layout web content template & input valid value for field / - Click Save	New Free layout web content is created	High	WCM-2727 / CCP-346	After step 6: go to /classic/home ==> old content is shown instead of new one (in edit mode you can see the new content)
	REG_AIO165_WCM_002	001	REG_AIO165_WCM_002	Check if the content edition is considered after publication	Step 2: Edit content	- Select new added web content / - Click Edit document in Action bar / - Make changes for the web content	Changes are saved	High	WCM-2727 / CCP-346
	REG_AIO165_WCM_002	001	REG_AIO165_WCM_002	Check if the content edition is considered after publication	Step 3: Edit status to publish	- Click Manage Publication from Action bar / - Click Live to change status	Change status successfully (Enrolled is marked)	High	WCM-2727 / CCP-346
	REG_AIO165_WCM_002	001	REG_AIO165_WCM_002	Check if the content edition is considered after publication	Step 4: Add node to a page (/classic/home for example)	- Choose Publication Pages tab / - Select page from left pane then click → button	Path of selected page is displayed in right pane & the web content is displayed in selected page	High	WCM-2727 / CCP-346
	REG_AIO165_WCM_002	001	REG_AIO165_WCM_002	Check if the content edition is considered after publication	Step 5: Edit content again	In Site Explorer: edit content of above web content	Changes is saved (status of current version is draft)	High	WCM-2727 / CCP-346
	REG_AIO165_WCM_002	001	REG_AIO165_WCM_002	Check if the content edition is considered after publication	Step 6: Publish the node again	In SIte Explorer: / - Click Manage Publication / - Click Live to change status	go to /classic/home: the content is updated with the new edited (both view/edit mode)	High	WCM-2727 / CCP-346
003	REG_AIO165_WCM_004	001	REG_AIO165_WCM_004	Check if Newsletter mail's validator allows a multiple domain names in address mail	Step 1: Show Newsletters page	Go to Acme->newsletters	Newsletters page is shown correctly	High	WCM-2782 / CCP-386	A Popup appears with Email address is invalid! message.
	REG_AIO165_WCM_004	001	REG_AIO165_WCM_004	Check if Newsletter mail's validator allows a multiple domain names in address mail	Step 2: Subscribe mail	- Input value into "Your Email" field like: user@domain1.domain2.fr / - Tick the check-box corresponding to your chosen subscription / - Click Subscribe	Show popup alert subscribe mail successfully	High	WCM-2782 / CCP-386
004	REG_AIO165_WCM_005	001	REG_AIO165_WCM_005	Check when publish content after image resize with Shift button pressed	Step 1: Create new content with image	- Go to Site Explorer / - Go to acme/web content / - Click Add document in action bar / - Select 1 template / - Input valid value for fields / - In the CK Editor: Click icon to insert image / - Select path from left pane / - Upload 1 image / - Select uploaded image to add into the web content / - Save	New web content added with image	High	ALL-295, WCM-2715, PORTAL-3783 / CCP-329	IE 7 crash when publishing content after image resize with Shift button pressed
	REG_AIO165_WCM_005	001	REG_AIO165_WCM_005	Check when publish content after image resize with Shift button pressed	Step 2: Resize the image	- Select added web content to view / - Click Edit document / - Resize the image / - Click Save	The image in the content is resized	High	ALL-295, WCM-2715, PORTAL-3783 / CCP-329
005	REG_AIO165_WCM_006	001	REG_AIO165_WCM_006	Label categories are not traduced in clv edition	Step 1: Change language	Go to Language Setting & select 1 language to display	The site is displayed in new selected language	High	WCM-2787, WCM-2781, WCM-2786 / CCP-384	Categories' labels are not translated in CLV edition:
	REG_AIO165_WCM_006	001	REG_AIO165_WCM_006	Label categories are not traduced in clv edition	Step 2: Show CLV config form	- Go to Site Editor --> Add Page Wizard / - Input valid value then go to step 3 in wizard / - Drag & drop Content List portlet into page / - Click Edit portlet icon	CLV config form is shown	High	WCM-2787, WCM-2781, WCM-2786 / CCP-384
	REG_AIO165_WCM_006	001	REG_AIO165_WCM_006	Label categories are not traduced in clv edition	Step 3: Check displaying label in new selected language	- Choose Manual mode then click + icon to Select folder part	The every label is well translated	High	WCM-2787, WCM-2781, WCM-2786 / CCP-384
006	REG_AIO165_WCM_007	001	REG_AIO165_WCM_007	Check viewing localised content	Step 1: Add view into Site Explorer	- Login by admin / - Go to Site Administrator / - Manage drive / - Edit 1 drive that you are going to use (e.g: Manage site): add more view (admin view, simple view, system view)	Edit successfully	High	WCM-2628 / CCP-247	when i try to view the content in translated language i get the following error in the console: / [ERROR] portal:Lifecycle - template : /exo:ecm/templates/exo:webContent/views/vi / ew1 <javax.jcr.PathNotFoundException: Node not found /sites content/live/redhat/ / web contents/News/languages/fr/default.html/jcr:content>javax.jcr.PathNotFoundEx / ception: Node not found /sites content/live/redhat/web contents/News/languages/f / r/default.html/jcr:content
	REG_AIO165_WCM_007	001	REG_AIO165_WCM_007	Check viewing localised content	Step 2: Add content	Go to Site Explorer -> Sites Management under /acme create new content	Add new content successfully	High	WCM-2628 / CCP-247
	REG_AIO165_WCM_007	001	REG_AIO165_WCM_007	Check viewing localised content	Step 3: Set localize for added content	- Select to view added content / - Go to Collaboration → Add/edit localized contents from Action bar / - Select new language & input valid value for field in new selected language	New added language is listed in Language drop down list in View Language tab	High	WCM-2628 / CCP-247
	REG_AIO165_WCM_007	001	REG_AIO165_WCM_007	Check viewing localised content	Step 4: View content in new language	- Choose new added language from list then click View	The content is display well in selected language	High	WCM-2628 / CCP-247
007	REG_AIO165_WCM_008	001	REG_AIO165_WCM_008	Check translation of results' number after search	Step 1: Change language	- Go to Language Settings & select a language to view	The site is displayed in new selected language	Low	ALL-328, WCM-2757 / CCP-377	When you make a search which results take many pages, the message at right top is not correctly translated in French. / "Résultats 1 - 5 d'environ 35 pour test (0.079 seconde)" should be "Résultats 1 - 5 sur 35 pour test (0.079 seconde) "
	REG_AIO165_WCM_008	001	REG_AIO165_WCM_008	Check translation of results' number after search	Step 2: Search	Make a search which results take many pages by input text into quick search textbox & enter	The message at right top is correctly in new selected language	Low	ALL-328, WCM-2757 / CCP-377
008	REG_AIO165_WCM_009	001	REG_AIO165_WCM_009	Search result - wrong traduction when there's no result	Step 1: Change language	- Go to Language Settings & select a language to view	The site is displayed in new selected language	Low	ALL-327, WCM-2754 / CCP-373	When a search has no result, the traduction for message is wrong (no_result.png). / It is : Votre recherche ijij - ne correspond à aucun documentandpage / It should be : Votre recherche ijij - ne correspond à aucun document et page
	REG_AIO165_WCM_009	001	REG_AIO165_WCM_009	Search result - wrong traduction when there's no result	Step 2: Search	Make a search that return no result	Message is display correctly	Low	ALL-327, WCM-2754 / CCP-373
009	REG_AIO165_WCM_010	001	REG_AIO165_WCM_010	Check translation of label in the “Form Generator” portlet	Step 1: Change language	- Go to Language Settings & select a language to view	The site is displayed in new selected language	Low	WCM-2755 / CCP-374	The title of the tab should be "Constructeur de formulaire" instead of "Formulaire de constructeur".
	REG_AIO165_WCM_010	001	REG_AIO165_WCM_010	Check translation of label in the “Form Generator” portlet	Step 2: Show “Form Generator” portlet	Go to Groups → Form Generator	The labels are well translated	Low	WCM-2755 / CCP-374
010	REG_AIO165_WCM_011	001	REG_AIO165_WCM_011	Mistakes in french internationalization	Step 1: Check translation of label in some forms when add new SCV	- Go to Language Setting then select a language to display / - Go to Site Editor --> Add content	Add new content form is shown. Do some next steps to complete adding new SCV to check if all labels are well translated in selected language	High	WCM-2687 / CCP-300	Add SCV welcome form: / Abort = Annuler / Bienvenue à SCV = Bienvenue dans SCV / Créer de nouveaux contenus = Créer un nouveau contenu / Add SCV select layout form: / Abort = Annuler / Sous forme de modèle = Suivant un modèle / Ideally: translate the labels in the layout selectbox / Newsletter Manager/Add new category form: / Redactor = Rédacteur / Save = Enregistrer / Cancel = Annuler / Add Newsletter form: / Advanced=Avancé
	REG_AIO165_WCM_011	001	REG_AIO165_WCM_011	Mistakes in french internationalization	Step 2: Check translation of label in Add new subscription form (Newsletter)	- Go to Newsletter Manager / - Click New subscription	Add new subscription form is shown with all labels are well translated in selected language	High	WCM-2687 / CCP-300
	REG_AIO165_WCM_011	001	REG_AIO165_WCM_011	Mistakes in french internationalization	Step 3: Check translation of label in Add new letter form	- Go to Newsletter Manager / - Click Newsletter	Add new letter form is shown with all label are well translated in selected language	High	WCM-2687 / CCP-300
011	REG_AIO165_WCM_012	001	REG_AIO165_WCM_012	Check Sorting Mechanism	Step 1: Create node	- Login by admin / - Go to Site Explorer → Site Management / - Create a folders and documents list	Create successfully	High	WCM-2728 / CCP-347	Currently: / stack-trace / /////////// / javax.jcr.RepositoryException: Unknown type -1 / at org.exoplatform.ecm.webui.comparator.PropertyValueComparator.compare(PropertyValueComparator.java:70) / at
	REG_AIO165_WCM_012	001	REG_AIO165_WCM_012	Check Sorting Mechanism	Step 2: Sort the list	- Sort the list (by title, date, author, status)	Sort successfully	High	WCM-2728 / CCP-347
012	REG_AIO165_WCM_014	001	REG_AIO165_WCM_014	Check showing webcontent by category (presentation portlet)	Step 1: Add new taxonomy tree	- Login as admin (root) / - Go to Sites Administration ->Manage Taxonomy Trees / - Click Edit icon at acme line / - Click Add icon in Action column / - Input Name for new taxonomy & click Save (under acme add new taxonomy tree.) / - Click close the Edit taxonomy tree form	New taxonomy tree is added successfully under the acme	High	WCM-2744 / CCP-359	After step 4: The content is not exist in this page and we got an exception
	REG_AIO165_WCM_014	001	REG_AIO165_WCM_014	Check showing webcontent by category (presentation portlet)	Step 2: Add new content in Site Explorer	- Go to Site explorer and then Sites management / - Select acme node from left pane / - Click Add document / - Select 1 web content template / - Input needed value in fields (the name must begin with "acme" for example type "acmeexample" as name.) / - Click Save	New content is added	High	WCM-2744 / CCP-359
	REG_AIO165_WCM_014	001	REG_AIO165_WCM_014	Check showing webcontent by category (presentation portlet)	Step 3: Add referenced category to new added web content	- Select to view new added content / - Click Manages Categories from Action bar then choose Select category tab / - Select acme from Taxonomy Tree drop down list / - Click icon in Action column at the line of new added taxonomy at Step 1 / - Click Close	- Selected taxonomy is listed in Referenced categories tab in Add category form	High	WCM-2744 / CCP-359
	REG_AIO165_WCM_014	001	REG_AIO165_WCM_014	Check showing webcontent by category (presentation portlet)	Step 4: View new added taxonomy at Step 1 in News page	Go to ACME site and select News page and then click on created category	The web content created above is displayed in right pane & there's no error in console	High	WCM-2744 / CCP-359
013	REG_AIO165_WCM_015	001	REG_AIO165_WCM_015	Check Manage taxonomy	Step 1: Add new taxonomy tree	- Login as admin (root) / - Go to Sites Administration ->Manage Taxonomy Trees / - Click Edit icon at acme line / - Click Add icon in Action column / - Input Name for new taxonomy / Must begin with "acme" for example put as name "acmetest". / - Click Save / - Click Close the Edit taxonomy tree form	New taxonomy tree is added successfully under the acme	High	WCM-2745 / CCP-360	After step 3: “acme” is listed in the Referenced categories tab in stead of “acmetest” / (=>this content will be created under acme and not acmetest. / under /acme/categories/acme we will find this content .)
	REG_AIO165_WCM_015	001	REG_AIO165_WCM_015	Check Manage taxonomy	Step 2: Add new content in Site Explorer	- Go to Site explorer and then Sites management / - Select acme node from left pane / - Click Add document / - Select 1 web content template / - Input valid value for fields / - Click Save	New content is added	High	WCM-2745 / CCP-360
	REG_AIO165_WCM_015	001	REG_AIO165_WCM_015	Check Manage taxonomy	Step 3: Add referenced category to new added web content	- Select to view new added content / - Click Manages Categories from Action bar then choose Select category tab / - Select acme from Taxonomy Tree drop down list / - Click icon in Action column at the line of new added taxonomy at Step 1	- Selected taxonomy is listed in Referenced categories tab in Add category form	High	WCM-2745 / CCP-360
014	REG_AIO165_WCM_016	001	REG_AIO165_WCM_016	Error while setting a page with PCLV portlet	Step 1: View News page	- Login as admin / - Go to ACME site -> Select News page.	News page is displayed	High	WCM-2753 / CCP-368	Currently at step 6 the Edit mode tab is blank, we cannot setting a new taxonomy tree. / And we got an exception
	REG_AIO165_WCM_016	001	REG_AIO165_WCM_016	Error while setting a page with PCLV portlet	Step 2: Show Edit page wizard	Go to Site Editor ->Edit Page.	Edit page wizard is shown currently at step 3	High	WCM-2753 / CCP-368
	REG_AIO165_WCM_016	001	REG_AIO165_WCM_016	Error while setting a page with PCLV portlet	Step 3: Edit page	- Click x icon at PCLV portlet (Parameterized) to delete it from this page / - Click Save to complete editing page	Edit page successfully	High	WCM-2753 / CCP-368
	REG_AIO165_WCM_016	001	REG_AIO165_WCM_016	Error while setting a page with PCLV portlet	Step 4: Delete acme category	Go to Site Explorer -> Sites Management under /acme/categories delete the acme category	acme category is deleted	High	WCM-2753 / CCP-368
	REG_AIO165_WCM_016	001	REG_AIO165_WCM_016	Error while setting a page with PCLV portlet	Step 5: Show Edit page wizard form again	- Select News page in acme site / - Select News page -> Site Editor -> Edit Page Wizard.	Edit page wizard is shown currently at step 2	High	WCM-2753 / CCP-368
	REG_AIO165_WCM_016	001	REG_AIO165_WCM_016	Error while setting a page with PCLV portlet	Step 6: Add PCLV portlet into page & config	- Drag & drop Category content portlet / - Click Edit portlet icon	Parameterized content list viewer configuration form is shown in Edit mode tab	High	WCM-2753 / CCP-368
015	REG_AIO165_WCM_017	001	REG_AIO165_WCM_017	Check Problem in downloading binary from PCLV	Step 1: Upload a binary	- Go to Site Explorer --> Site Management / - Upload 1 binary (.pdf) in to a category	Upload file successfully	High	WCM-2746 / CCP-362	# try to download it, oups, you can not, the link points to jcr:frozeNode / # Go in Edit_MODE, and try to download the document / # It is working, the file is downloaded
	REG_AIO165_WCM_017	001	REG_AIO165_WCM_017	Check Problem in downloading binary from PCLV	Step 2: Change status to public	- Select uploaded file / - Click Manage Publication / - Change to Live	Change status successfully (Enrolled is marked)	High	WCM-2746 / CCP-362
	REG_AIO165_WCM_017	001	REG_AIO165_WCM_017	Check Problem in downloading binary from PCLV	Step 3: Add referenced category	- Choose Manage category from Action bar and add it into a category (e.g:acme/World)	Add success	High	WCM-2746 / CCP-362
	REG_AIO165_WCM_017	001	REG_AIO165_WCM_017	Check Problem in downloading binary from PCLV	Step 4: View the uploaded content in page	- Choose News page in acme site / - Choose category at step 3 (World) / - Click to view the uploaded file in the right pane	The file is shown	High	WCM-2746 / CCP-362
	REG_AIO165_WCM_017	001	REG_AIO165_WCM_017	Check Problem in downloading binary from PCLV	Step 5: Down load file	Click on Download this file link	The file is downloaded	High	WCM-2746 / CCP-362
016	REG_AIO165_WCM_018	001	REG_AIO165_WCM_018	Check Problem with "Add a site page link " on FCKEDITOR	Step 1: Show form to edit SCV portlet	- Login by root / - Go to acme site / - Turn on edit mode / - Click Edit icon at 1 SCV portlet (e.g: banner)	Edit form is shown	Low	WCM-2717 / CCP-332	With Firefox every thing works well but with Internet Explorer 8 the href area is very short and it's difficult to find where to click
	REG_AIO165_WCM_018	001	REG_AIO165_WCM_018	Check Problem with "Add a site page link " on FCKEDITOR	Step 2: Show form to Insert link to site page	In the FCKEDITOR: click the icon Insert link to site page	The form is well displayed	Low	WCM-2717 / CCP-332
017	REG_AIO165_WCM_019	001	REG_AIO165_WCM_019	Check play a media file that was published into a page	Step 1: Upload file	- Go to Site Explorer --> Site Management / - Upload 1 media file into a category (/classic/medias/videos/)	Upload file successfully	Low	WCM-2723 / CCP-344	The file can not be opened
	REG_AIO165_WCM_019	001	REG_AIO165_WCM_019	Check play a media file that was published into a page	Step 2: Public file	- Select uploaded file / - Choose Manage Publication then change status to Live / - In Publication pages tab: select 1 page to public this file	Public file successfully	Low	WCM-2723 / CCP-344
	REG_AIO165_WCM_019	001	REG_AIO165_WCM_019	Check play a media file that was published into a page	Step 3: Check using published file in page	- Open selected page at step 2 / - Try to play the media file	The file is done	Low	WCM-2723 / CCP-344
018	REG_AIO165_WCM_020	001	REG_AIO165_WCM_020	Check listing content to be displayed in SCV when switch the filter condition	Step 1: Create folder	- Go in the file explore and create a folder	Folder is created	Low	WCM-2788 / CCP-392	The content in the right pane is not updated, user have to click on the folder again to see it
	REG_AIO165_WCM_020	001	REG_AIO165_WCM_020	Check listing content to be displayed in SCV when switch the filter condition	Step 2: Create web content	- Select added folder & add 1 content (document) into it	Content is added	Low	WCM-2788 / CCP-392
	REG_AIO165_WCM_020	001	REG_AIO165_WCM_020	Check listing content to be displayed in SCV when switch the filter condition	Step 3: Upload file	- Upload 1 file into above folder	Upload file successfully	Low	WCM-2788 / CCP-392
	REG_AIO165_WCM_020	001	REG_AIO165_WCM_020	Check listing content to be displayed in SCV when switch the filter condition	Step 4: Add SCV page	- Go to Site Editor --> Add page wizard / - At step 3: drag & drop Single Content Viewer portlet into page	Drag & drop successfully	Low	WCM-2788 / CCP-392
	REG_AIO165_WCM_020	001	REG_AIO165_WCM_020	Check listing content to be displayed in SCV when switch the filter condition	Step 5: Edit SCV portlet	- Click Edit icon to edit SCV portlet	Edit form is shown	Low	WCM-2788 / CCP-392
	REG_AIO165_WCM_020	001	REG_AIO165_WCM_020	Check listing content to be displayed in SCV when switch the filter condition	Step 6: Config SCV by selecting exiting content	- In Welcome to Single Content Viewer form: choose Select a content / - In the Content Browser tab: select path to added folder at step 1	The content created at step 2 is listed in right pane	Low	WCM-2788 / CCP-392
	REG_AIO165_WCM_020	001	REG_AIO165_WCM_020	Check listing content to be displayed in SCV when switch the filter condition	Step 7: Switch the filter	Switch the filter by selecting Media for Filter by	The content listed in right pane is replaced by the uploaded file at step 3	Low	WCM-2788 / CCP-392
019	REG_AIO165_WCM_021	001	REG_AIO165_WCM_021	Check display a link in a content	Step 1: Create content	- Go to Site Explorer --> Site management / - Select a category & create 1 document with link in content	Create new content successfully	High	WCM-2227 / CCP-328	The link is display without underline
	REG_AIO165_WCM_021	001	REG_AIO165_WCM_021	Check display a link in a content	Step 2: View added content	Select added content to view	The link in the content is display with the underline	High	WCM-2227 / CCP-328
020	REG_AIO165_WCM_022	001	REG_AIO165_WCM_022	Check when select content from search result to view in CLV	Step 1: Show form to edit CLV portlet	- Select Home page in acme site / - Turn on edit mode / - Click Preference icon at a CLV (Documents or Latest News)	Edit form is shown	High	WCM-2751 / CCP-371	error in UI after step 4
	REG_AIO165_WCM_022	001	REG_AIO165_WCM_022	Check when select content from search result to view in CLV	Step 2: Show form to select path	- Choose the By content / - Click on the select folder path icon	Multiple Content Select panel is shown	High	WCM-2751 / CCP-371
	REG_AIO165_WCM_022	001	REG_AIO165_WCM_022	Check when select content from search result to view in CLV	Step 3: Select content	- Select a content from the content browser / - Save	Selected content is listed	High	WCM-2751 / CCP-371
	REG_AIO165_WCM_022	001	REG_AIO165_WCM_022	Check when select content from search result to view in CLV	Step 4: Search content	- Click on the select folder path icon again / - Use content search form tab to search on content / -Choose the search result to introduce it in the content list	Chosen content from search result is listed	High	WCM-2751 / CCP-371
021	REG_AIO165_WCM_023	001	REG_AIO165_WCM_023	Inversion of content's list in CLV at every validation	Step 1: Create document	- Go to site Explorer → Site Management / - Create some documents (doc1, doc2, doc3)	Create document successfully	High	WCM-2721 / CCP-343	1/Create a page and include a Portlet CLV in it. / 2/Configure the CLV in manual mode and add in it 3 documents: Doc1,Doc2 and Doc3 / 3/Validate the CLV+ the page / => The CLV shows these documents in this order: Doc3, Doc2 and Doc3, but, it is expected to have :Doc1, Doc2 and Doc 3 / * / Using now the edit mode and edit the CLV =>the list appears in this order: Doc3, Doc2, Doc1. But, if you validate (without modifying neither the order, nor anything else), this same list appears in this order: Doc1, Doc2, Doc3
	REG_AIO165_WCM_023	001	REG_AIO165_WCM_023	Inversion of content's list in CLV at every validation	Step 2: Create page	Create a page includes a Portlet CLV in it.	Create new page successfully	High	WCM-2721 / CCP-343
	REG_AIO165_WCM_023	001	REG_AIO165_WCM_023	Inversion of content's list in CLV at every validation	Step 3: List added document into created page	- Turn on edit mode / - Click Quick Edit icon to show Edit above CLV portlet in added page / - Choose Manual mode & click + icon to show form to select document / - Select category that contain created documents at step 1 / - Choose document to displayed from right pane / - Click Save	Selected documents are listed (by order: doc1, doc2, doc3)	High	WCM-2721 / CCP-343
	REG_AIO165_WCM_023	001	REG_AIO165_WCM_023	Inversion of content's list in CLV at every validation	Step 4: Change the order be documents that will be displayed	- Click Edit icon again / - Do not make any change / - Click Save	The order of document has no change	High	WCM-2721 / CCP-343
022	REG_AIO165_WCM_024	001	REG_AIO165_WCM_024	Changes in FCC action's parameters are not taken in consideration	Step 1: Add FCC page	- Go to Site Editor --> Add New Page / - At step 3: Drag & drop FCC portlet into page	FCC portlet is displayed in right pane at step 3	High	WCM-2689, ECM-5237 / CCP-303	When executing the FCC, sendMailAction took the first mail added as send mail to parameter . / The new values are taken in consideration after restarting the server.
	REG_AIO165_WCM_024	001	REG_AIO165_WCM_024	Changes in FCC action's parameters are not taken in consideration	Step 2: Config FCC	- Click Edit at the top right corner of FCC portlet / - Select locate to save is Group/platforms/users/documents / - Click on Add Action icon / - Add “exo:SendMailAction” with a specific email address (mail1) (Life cycle: add) / - Click Save to complete adding new page	Add action successfully	High	WCM-2689, ECM-5237 / CCP-303
	REG_AIO165_WCM_024	001	REG_AIO165_WCM_024	Changes in FCC action's parameters are not taken in consideration	Step 3: Add document using FCC	In new added FCC page: Input valid values & click Save to add new document	An email is sent to registered email (mail 1) when add action	High	WCM-2689, ECM-5237 / CCP-303
	REG_AIO165_WCM_024	001	REG_AIO165_WCM_024	Changes in FCC action's parameters are not taken in consideration	Step 4: Change registered email	- Edit FCC portlet again --> Edit added action with new email address (mail2)	Change is saved	High	WCM-2689, ECM-5237 / CCP-303
	REG_AIO165_WCM_024	001	REG_AIO165_WCM_024	Changes in FCC action's parameters are not taken in consideration	Step 5: Check sending mail after editing FCC	Use FCC page to create another document	An email is sent to new-registered email (mail 2)	High	WCM-2689, ECM-5237 / CCP-303
023	REG_AIO165_WCM_025	001	REG_AIO165_WCM_025	Check if Searched texts in search results are highlighted	Step 1: Search	- Login / - Input text in search text box in the top right screen / - Hit the enter	- The result is returned / - The search keyword is highlighted in the result	High	WCM-2822 / CCP-426

## Bugs_v1_6_6
	TEST CASES					Passed	Passed	0	0	0	0
				Failed	Failed	0	0	0	0
	Function List:	Bugs on WCM 1.2.x for regression test					Blocked	Blocked	0	0	0	0
	Total Main Cases:	18					Untested	Untested	0	0	0	0
				N/A	N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
001	REG_AIO166_WCM_001	001	REG_AIO166_WCM_001	Check when browsing directories with special characters while configuring content detail (IE7)	Step 1: Add category	In IE7 / - Login by admin / - Go to Sites Explorer/acme / - Create category & sub category with names containing characters like the "é"	Create new category successfully	High	WCM-2816 / CCP-422
	REG_AIO166_WCM_001	001	REG_AIO166_WCM_001	Check when browsing directories with special characters while configuring content detail (IE7)	Step 2: Create new page contain content detail	- Go to Site Editor/Add page wizard / - Input valid values then go to step 3 / - Drag & drop content detail portlet into page	SCV portlet is added into page	High	WCM-2816 / CCP-422
	REG_AIO166_WCM_001	001	REG_AIO166_WCM_001	Check when browsing directories with special characters while configuring content detail (IE7)	Step 3: Edit content detail	- Click icon to edit content detail portlet / - Choose Select a content / - Browse to select content. Select the previously added directory	Directory is selected	High	WCM-2816 / CCP-422	Can not select, there's error in UI
002	REG_AIO166_WCM_002	002	REG_AIO166_WCM_002	Check when browsing directories with special characters while configuring CLV (IE7)	Step 1: Add folders	In IE7 / - Login by admin / - Go to Sites Explorer/acme / - Create folder & sub folder with names containing characters like the "é"	Create new folders successfully	High	WCM-2816 / CCP-422
	REG_AIO166_WCM_002	002	REG_AIO166_WCM_002	Check when browsing directories with special characters while configuring CLV (IE7)	Step 2: Create new page contain CLV	- Go to Site Editor/Add page wizard / - Input valid values then go to step 3 / - Drag & drop CLV portlet into page	CLV portlet is added into page	High	WCM-2816 / CCP-422
	REG_AIO166_WCM_002	002	REG_AIO166_WCM_002	Check when browsing directories with special characters while configuring CLV (IE7)	Step 3: Edit CLV	- Click icon to edit CLV portlet / - Click Select folder path icon / - Browse to select content. Select the previously added directory	Directory is selected	High	WCM-2816 / CCP-422	Can not select, there's error in UI
003	REG_AIO166_WCM_003	001	REG_AIO166_WCM_003	Check listing document with special character in name in CLV	Step 1: Go to Sites Explorer	- Login / - Go to Sites Explorer/Sites management/acme/documents	Documents is selected	High	WCM-2795 / CCP-405
	REG_AIO166_WCM_003	001	REG_AIO166_WCM_003	Check listing document with special character in name in CLV	Step 2: Upload file	Upload a binary with name containing character like '	Upload is done	High	WCM-2795 / CCP-405
	REG_AIO166_WCM_003	001	REG_AIO166_WCM_003	Check listing document with special character in name in CLV	Step 3: Public uploaded file	- Select to view uploaded file / - Click Manage Publications / - Click on Live to public the file	Uploaded file is changed status	High	WCM-2795 / CCP-405
	REG_AIO166_WCM_003	001	REG_AIO166_WCM_003	Check listing document with special character in name in CLV	Step 4: Check showing uploaded file	Go to Overview page in acme site	Uploaded file is listed in Documents list with correct name	High	WCM-2795 / CCP-405	a %27 replace the '
004	REG_AIO166_WCM_004	001	REG_AIO166_WCM_004	Check order content in CLV using manual browse	Step 1: Go to ACME site	- Login by admin / - Select acme site / - Switch to edit mode	Edit mode in acme site is displayed, there's Quick Edit icon for each portlet in the page	High	WCM-2818 / CCP-424
	REG_AIO166_WCM_004	001	REG_AIO166_WCM_004	Check order content in CLV using manual browse	Step 2: Show form to edit a CLV	Click Quick edit icon at a CLV (e.g: Document)	CLV edit form is shown	High	WCM-2818 / CCP-424
	REG_AIO166_WCM_004	001	REG_AIO166_WCM_004	Check order content in CLV using manual browse	Step 3: Select document	Choose the manual browse and select a multiple contents for example: / /sites content/live/acme/categories/acme/News1 / /sites content/live/acme/categories/acme/News3 / /sites content/live/acme/categories/acme/News4	Selected documents are listed as 1, 3, 4 in CLV config form	High	WCM-2818 / CCP-424
	REG_AIO166_WCM_004	001	REG_AIO166_WCM_004	Check order content in CLV using manual browse	Step 4: Change order of document in list	In CLV config form / Use the Up/Down arrows to change their position	The order is changed	High	WCM-2818 / CCP-424
	REG_AIO166_WCM_004	001	REG_AIO166_WCM_004	Check order content in CLV using manual browse	Step 5: Check listing document after editing the config	Click Save in Edit CLV form	Selected documents are listed as changed at step 4	High	WCM-2818 / CCP-424	1. After saving, the order is not respected in the clv display / 2. Edit again and change positions, the problem still occurs.
005	REG_AIO166_WCM_005	001	REG_AIO166_WCM_005	Check search when result exceeds 250	Step 1: Add document	- Login / - Go to Site Explorer/Sites Management/acme/documents / - Create/Upload or use web dav to add 250 documents with the same name	250 documents are added	High	WCM-2828 / CCP-429
	REG_AIO166_WCM_005	001	REG_AIO166_WCM_005	Check search when result exceeds 250	Step 2: Quick Search	- Back to Home page / - Input added file name into search text box & hit enter	Go to Search portlet with search result in pages	High	WCM-2828 / CCP-429	- Only the first page results are displayed.
006	REG_AIO166_WCM_006	001	REG_AIO166_WCM_006	Check internationalized label in WCMInsertContent functionality	Step 1: Show Add new Free layout webconntent form	- Login / - Go to Site explorer / - Select any driver / - Add new document is Free layout webcontent	Add new free layout content is shown	Low	WCM-2853 / CCP-474
	REG_AIO166_WCM_006	001	REG_AIO166_WCM_006	Check internationalized label in WCMInsertContent functionality	Step 2: Show Insert content form	Click on the WCMInsertContent icon in the FCKEditor of the main content	Insert content form is shown	Low	WCM-2853 / CCP-474
	REG_AIO166_WCM_006	001	REG_AIO166_WCM_006	Check internationalized label in WCMInsertContent functionality	Step 3: Change language	- Keep the forms open / - Change displaying language	Labels in form are translated into new selected language	Low	WCM-2853 / CCP-474	Labels are not internationalized in the categories' navigation (General drives, There is no content...)
007	REG_AIO166_WCM_007	001	REG_AIO166_WCM_007	Check if links Next & Previous in search portlet are internationalized	Step 1: Change language	- Login / - Click icon at the top left of screen & select Language Settings / - Select another language to view page	Page is displayed in new selected language	Low	WCM-2844 / CCP-459
	REG_AIO166_WCM_007	001	REG_AIO166_WCM_007	Check if links Next & Previous in search portlet are internationalized	Step 2: Search	- Input text into search text box & hit enter	- Search result is returned, all label in result form is translated in current using language (Next & Previous)	Low	WCM-2844 / CCP-459	In French, Next & Previous should be: Précédent, Suivant
008	REG_AIO166_WCM_008	001	REG_AIO166_WCM_008	Check insert link to a site page when add new web content	Step 1: Add new node	- Login by admin / - Go to Site Editor/Edit navigation / - Right click on blank area and select Add node (to add node at root path) / - Input Node name & do not select any page / - Click Save	New node is added	High	WCM-2843 / CCP-454
	REG_AIO166_WCM_008	001	REG_AIO166_WCM_008	Check insert link to a site page when add new web content	Step 2: Add sub node	- Right click on new added node & add new sub node with a specific page	Add node with page successfully	High	WCM-2843 / CCP-454
	REG_AIO166_WCM_008	001	REG_AIO166_WCM_008	Check insert link to a site page when add new web content	Step 3: Add web content	- Go to site explorer / - Select any driver / - Add document is Free layout webcontent / - Input Title and select a layout then click Save	Add new content with corresponding layout form is shown	High	WCM-2843 / CCP-454
	REG_AIO166_WCM_008	001	REG_AIO166_WCM_008	Check insert link to a site page when add new web content	Step 4: Show form to select link	- In the FCK editor toolbar click on the Insert link to a site page / - Click Get Portal Link	A form to select appears	High	WCM-2843 / CCP-454
	REG_AIO166_WCM_008	001	REG_AIO166_WCM_008	Check insert link to a site page when add new web content	Step 5: Select page	- Go to path of added node at step 1 & 2	The parent node (without page) is shown but it can not be selected to add into content. Its sub node is listed, the sub node can be added into content	High	WCM-2843 / CCP-454
009	REG_AIO166_WCM_009	001	REG_AIO166_WCM_009	Check showing sub node on admin bar when parent does not select to any page	Step 1: Add parent node	- Login by admin / - Go to Site Editor/Edit navigation / - Right click on blank area and select Add node (to add node on root path of current using portal) / - Input Node name & click Save (do not select any page)	Node is added	High	WCM-2842 / CCP-453
	REG_AIO166_WCM_009	001	REG_AIO166_WCM_009	Check showing sub node on admin bar when parent does not select to any page	Step 2: Add sub node	- Right click on new added node & select Add node / - Input node Name / - Select exiting page for node / - Click Save	New node with page is added	High	WCM-2842 / CCP-453
	REG_AIO166_WCM_009	001	REG_AIO166_WCM_009	Check showing sub node on admin bar when parent does not select to any page	Step 3: View in admin bar	- Click Save & Finish icon to quit Edit navigation form	- Added nodes (parent & child nodes) are listed in Admin bar	High	WCM-2842 / CCP-453	Parent node without page is not shown, so that can not see child node with page
010	REG_AIO166_WCM_010	001	REG_AIO166_WCM_010	Check downloading file with name containing an illegal jcr char	Step 1: Upload file	- Login / - Go to Sites Explorer/Site Management/acme/documents / - Upload 1 file with ' in name	Upload is done	Low	WCM-2832 / CCP-404
	REG_AIO166_WCM_010	001	REG_AIO166_WCM_010	Check downloading file with name containing an illegal jcr char	Step 2: Download file	In the right tree (wcm-view), right click on the Uploaded file and select "Download And Allow Edition"	File is downloaded	Low	WCM-2832 / CCP-404	Select "Download And Allow Edition": no response
011	REG_AIO166_WCM_011	002	REG_AIO166_WCM_011	Check if labels in right click menu in Sites Explorer are translated	Step 1: Change language	- Login / - Click on Language settings / - Select 1 language to view	Current portal is displayed in new selected language	Low	WCM-2832 / CCP-404
	REG_AIO166_WCM_011	002	REG_AIO166_WCM_011	Check if labels in right click menu in Sites Explorer are translated	Step 2: Check internationalization label	- Go to Sites Explorer/Sites Management / - Right click on 1 node	All labels are well translated	Low	WCM-2832 / CCP-404	"Download And Allow Edition" is not translated
012	REG_AIO166_WCM_012	001	REG_AIO166_WCM_012	Check WCMInsertContent when browsing directories with special characters	Step 1: Add folder	- Login / - Goto Sites Explorer → Sites Managemnt → Acme → Documents / - Add new folder with name contain special character (e.g: testé)	New folder is added	High	WCM-2861 / CCP-496
	REG_AIO166_WCM_012	001	REG_AIO166_WCM_012	Check WCMInsertContent when browsing directories with special characters	Step 2: Upload file	- Select added folder / - Upload 1 image	Upload is done	High	WCM-2861 / CCP-496
	REG_AIO166_WCM_012	001	REG_AIO166_WCM_012	Check WCMInsertContent when browsing directories with special characters	Step 3: Show add content form	- Go to Home page / - Click Site Editor/Add content / - Select Create new content / - Input title / - Select Free layout webcontent	Add free layout web content form is shown	High	WCM-2861 / CCP-496
	REG_AIO166_WCM_012	001	REG_AIO166_WCM_012	Check WCMInsertContent when browsing directories with special characters	Step 4: Select content	- In the Fckeditor of this newly added content select WCInsertContent Icon / - Browse General drives → Sites Management → Acme → Documents->testé	Uploaded image is not listed in right pane. It is listed if filter to view by Medias	High	WCM-2861 / CCP-496	Error in console / DriverConnector - Error when perform getFoldersAndFiles: <javax.jcr.PathNotFoundException: Item not found /sites content/live/acme/documents/test? in workspac / e collaboration>javax.jcr.PathNotFoundException: Item not found /sites content/live/acme/documents/test? in workspace collaboration
013	REG_AIO166_WCM_013	002	REG_AIO166_WCM_013	Check when select drive with special character	Step 1: Add drive	- Login by admin / - Go to Group → Site Administration / - Select Content presentation → Manage Drives / - Click Add Drive / - Input testéDrive for Name / - Select collaboration for Workspace / - Root path for Home path / - Choose Any permission for Permission / - Choose Show side bar option / - Select Admin View and Simple View / - Save	New drive Is added	High	WCM-2861 / CCP-496
	REG_AIO166_WCM_013	002	REG_AIO166_WCM_013	Check when select drive with special character	Step 2: Add content	- Go to Sites Explorer --> Sites Management / - Select acme → documents / - Click Add document / - Choose Free Layout webcontent template / - In Main content CK: click InsertContent icon / - In the tree explorer select the "testéDrive"	The "testéDrive" is selected properly	High	WCM-2861 / CCP-496	Exception in console / [ERROR] DriverConnector - Error when perform getFoldersAndFiles: <java.lang.NullPointerException>java.lang.NullPointerException / at org.exoplatform.wcm.connector.fckeditor.DriverConnector.getFoldersAndFiles(DriverConnector.java:198)
014	REG_AIO166_WCM_014	001	REG_AIO166_WCM_014	Check search with accented characters	Step 1: Add document	- Login acme site / - Go to Sites Explorer/Sites Management/acme/documents / - Create new article with word Téléphone	Article is added	High	WCM-2860 / CCP-495
	REG_AIO166_WCM_014	001	REG_AIO166_WCM_014	Check search with accented characters	Step 2: Public the article	- If there's no Manage Publication in action bar in Site management drive: Go to Sites Administration to Edit Manage Sites drive & Add Admin view / - Select added article / - Click Manage Publication in Action bar & click Live icon to change article status	Article is published	High	WCM-2860 / CCP-495
	REG_AIO166_WCM_014	001	REG_AIO166_WCM_014	Check search with accented characters	Step 3: Search	Input the word Telephone into search textbox in banner & hit enter	Search result is returned with added article	High	WCM-2860 / CCP-495	the article is not mentioned in search result
015	REG_AIO166_WCM_015	001	REG_AIO166_WCM_015	Check removing container after being inserted in the page	Step 1: Show edit page form	- Login / - Go to Site Editor → Edit page wizard	Edit page by wizard is show	High	WCM-2821 / CCP-418
	REG_AIO166_WCM_015	001	REG_AIO166_WCM_015	Check removing container after being inserted in the page	Step 2: Add container into page	- Go to Step 3 of edit page wizard / - Drag & drop a container into page	Container is added into page	High	WCM-2821 / CCP-418
	REG_AIO166_WCM_015	001	REG_AIO166_WCM_015	Check removing container after being inserted in the page	Step 3: Delete container	- Click x icon at the top right of portlet / - Confirm	The container is removed from page	High	WCM-2821 / CCP-418	The newly added container can't be removed from the page. Customer ask for a way to do it.
016	REG_AIO166_WCM_016	001	REG_AIO166_WCM_016	Check Edit CLV in manual mode	Step 1: Show edit page form	- Login / - Go to Site Editor → Edit page	Edit page by wizard is show	Low	WCM-2863 / CCP-514
	REG_AIO166_WCM_016	001	REG_AIO166_WCM_016	Check Edit CLV in manual mode	Step 2: Add CLV into page	- Drag & drop Content List portlet into page	Portlet is added	Low	WCM-2863 / CCP-514
	REG_AIO166_WCM_016	001	REG_AIO166_WCM_016	Check Edit CLV in manual mode	Step 3: Edit CLV	- Click edit icon to edit added CLV portlet / - Select By content / - Select one content / - Save / - Close	Edit CLV form is closed	Low	WCM-2863 / CCP-514
	REG_AIO166_WCM_016	001	REG_AIO166_WCM_016	Check Edit CLV in manual mode	Step 4: Edit CLV again	- Click edit icon to edit added CLV portlet / - Click select path icon / - Delete added content / - Save / - Click OK in alert message (requires to select a content) / - Close with the upper-right corner cross / - Click Save / - Click Close	Edit CLV form is closed.	Low	WCM-2863 / CCP-514	Issue 1 : the background layer is still there / Issue 2 : the CLV is broken
017	REG_AIO166_WCM_017	001	REG_AIO166_WCM_017	Check showing uploaded file with illegal JCR characters in Name in Sites Explorer	Step 1: Upload file	- Go to Group/Sites Explorer / - Select Sites Management drive / - Choose acme/documents / - Click Upload icon in Action bar & select 1 file with name contains illegal JCR characters like ' from your local / - Click Upload icon / - Click Save	File is uploaded	High	WCM-2794 / CCP-403
	REG_AIO166_WCM_017	001	REG_AIO166_WCM_017	Check showing uploaded file with illegal JCR characters in Name in Sites Explorer	Step 2: View file	Double click on uploaded file to view its content	File is displayed with correct name	High	WCM-2794 / CCP-403	The nt:file view is shown and the illegal JCR chars are changed in %number(%27 for ')
018	REG_AIO166_WCM_018	001	REG_AIO166_WCM_018	Check Content Selector of CLV on IE7	Step 1: Add content	- Login by admin in IE7 / - Go to Sites Explorer → Sites Management → acme → web content / - Add new content, document or upload file	Nodes are added	High	WCM-2835 / CCP-443
	REG_AIO166_WCM_018	001	REG_AIO166_WCM_018	Check Content Selector of CLV on IE7	Step 2: Add page with CLV portlet	- Click Site Editor --> Create page wizard / - At Step 3: Drag & drop CLV (Content List) portlet into page	Portlet is added	High	WCM-2835 / CCP-443
	REG_AIO166_WCM_018	001	REG_AIO166_WCM_018	Check Content Selector of CLV on IE7	Step 3: Edit CLV	- Click icon to edit added CLV portlet	Edit CLV form is shown	High	WCM-2835 / CCP-443
	REG_AIO166_WCM_018	001	REG_AIO166_WCM_018	Check Content Selector of CLV on IE7	Step 4: Config CLV	- Choose Manual mode / - Click Select folder path icon / - In the Content browser tab browse path to added document/web content/uploaded file (General drives → / Sites Management → / Acme → / web contents)	All added document/web content/ uploaded file are listed in right pane	High	WCM-2835 / CCP-443
	REG_AIO166_WCM_018	001	REG_AIO166_WCM_018	Check Content Selector of CLV on IE7	Step 5: Change the filter	Select Media for filter field	All media files type (upload file, some kinds of document) are listed in right pane by Media filter	High	WCM-2835 / CCP-443	NOTHING HAPPENS

				d

				d

				d

## Bugs_v1_6_8
	TEST CASES					Passed	38	38	0	0	0
				Failed	2	2	0	0	0
	Function List:	Bugs on WCM 1.2.x for regression test					Blocked	0	0	0	0	0
	Total Main Cases:	21					Untested	0	0	0	0	0
				N/A	12	12	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
001	REG_AIO168_WCM_001	001	REG_AIO168_WCM_001	Check Download And Allow Edition from right-click menu in right pane on uploaded file with name containing a character like '	Step 1: Upload file	- Go to Sites Explorer/Sites Management/acme/document / - Select wcm-view. / - Upload 1 file with name containing character like '	File is uploaded	High	WCM-2832 / CCP-404		hanh.ly	Passed	Passed
	REG_AIO168_WCM_001	001	REG_AIO168_WCM_001	Check Download And Allow Edition from right-click menu in right pane on uploaded file with name containing a character like '	Step 2: Show Add category form	- Click + icon at List taxonomy / - Choose Select Category tab (if there's System taxonomy tree as default, you should login by admin, go to Sites Administration → Manage taxonomy → delete system taxonomy tree)	acme taxonomy tree is selected as default, all its taxonomies are listed below	High	WCM-2832 / CCP-404	acme taxonomy tree is selected but there's no sub taxonomy is listed	hanh.ly	Passed	Passed
002	REG_AIO168_WCM_002	001	REG_AIO168_WCM_002	Check showing News page after deleted acme category	Step 1: Show acme category	- Login by root / - Go to Sites Explorer/Sites Management / - Type "/acme/categories" at the address bar.	acme category is listed	High	WCM-2845 / CCP-465		hanh.ly	Passed	Passed
	REG_AIO168_WCM_002	001	REG_AIO168_WCM_002	Check showing News page after deleted acme category	Step 2: Delete acme category	- Right click on acme & select Delete / - Click OK to confirm	acme is deleted	High	WCM-2845 / CCP-465		hanh.ly	Passed	Passed
	REG_AIO168_WCM_002	001	REG_AIO168_WCM_002	Check showing News page after deleted acme category	Step 3: View News page	- Go to News page on acme site	News page is displayed & there's no error in console	High	WCM-2845 / CCP-465	Error in console	hanh.ly	Passed	Passed
003	REG_AIO168_WCM_003	001	REG_AIO168_WCM_003	Check while setting a page with PCLV portlet	Step 1: Show edit page wizard	- Go to ACME site -> Select News page. / - Go to Site Editor ->Edit Page Wizard. / - Go to step 3	Edit page at step 3 is shown in portlet mode	High	WCM-2753 / CCP-368		hanh.ly	Passed	Passed
	REG_AIO168_WCM_003	001	REG_AIO168_WCM_003	Check while setting a page with PCLV portlet	Step 2: Delete PCLV	- Click x icon to delete PCLV portlet (on the right, Category content) / - Click OK to confirm	Portlet is removed from page	High	WCM-2753 / CCP-368		hanh.ly	Passed	Passed
	REG_AIO168_WCM_003	001	REG_AIO168_WCM_003	Check while setting a page with PCLV portlet	Step 3: Delete acme category	Go to Sites Explorer/Sites Management under /acme/categories delete the acme category.	acme category is deleted	High	WCM-2753 / CCP-368		hanh.ly	Passed	Passed
	REG_AIO168_WCM_003	001	REG_AIO168_WCM_003	Check while setting a page with PCLV portlet	Step 4: Re-configure News page	- Select News page / - Go to Site Editor ->Edit Page Wizard. / - Go to step 3 / - Drag drop Category Content into page / - Click Edit icon to edit Category Content portlet	Edit portlet form is shown	High	WCM-2753 / CCP-368	Edit form is blank & exception in console	hanh.ly	Passed	Passed
004	REG_AIO168_WCM_004	001	REG_AIO168_WCM_004	Check if Link still be referenced after being inserted	Step 1: Show form to add free layout web content	- Go to Sites Explorer/Sites management/acme/document / - Click Add document then select Free layout web content template	Add Free layout web content form is shown	High	WCM-2872 / CCP-524		hanh.ly	Passed	Passed
	REG_AIO168_WCM_004	001	REG_AIO168_WCM_004	Check if Link still be referenced after being inserted	Step 2: Add content	- In the FCK: click Add link to a site page / - Click Get Portal link / - Browse a page / - Save	A link to selected page is added in the content	High	WCM-2872 / CCP-524		hanh.ly	Passed	Passed
	REG_AIO168_WCM_004	001	REG_AIO168_WCM_004	Check if Link still be referenced after being inserted	Step 3: Add more link	- Turn back to the beginning of the current line / - Click on enter 2 times. / - Move the cursor up to the first line / - Click Get Portal link or Insert/edit link / - Browse a page or input a link / - Save	New link is added. There're 2 different links in the content	High	WCM-2872 / CCP-524	There's only link added at step 3 with text of the link but the URL is the first added link. The first link was removed.	hanh.ly	Passed	Passed
005	REG_AIO168_WCM_005	001	REG_AIO168_WCM_005	Validate page acme/Overview by using W3C Validator	Step 1: Validate page acme/Overview	View source of acme/Overview & put in W3C Validator	No duplicated ID error	High	WCM-2936 / CCP-668	Line 2006, column 18: ID "UICLVPortlet" already defined / <div id="UICLVPortlet" class="UICLVPortlet"><span class="UIPopupContain... / Line 2236, column 18: ID "UICLVPortlet" already defined / <div id="UICLVPortlet" class="UICLVPortlet"><span class="UIPopupContain... / Line 2445, column 18: ID "UICLVPortlet" already defined / <div id="UICLVPortlet" class="UICLVPortlet"><span class="UIPopupContain...	hanh.ly	N/A	N/A
006	REG_AIO168_WCM_005	002	REG_AIO168_WCM_005	Validate new page with 2 category Navigation by using W3C Validtor	Step 1: Validate new page with 2 category Navigation	- Add new page ( AAA) / - Add at least 2 Category Navigation portlet to new page (AAA) / - Validate AAA by using W3C Validator	No duplicated ID error	High			hanh.ly	N/A	N/A
007	REG_AIO168_WCM_005	003	REG_AIO168_WCM_005	Validate new page with 2 category Content by using W3C Validtor	Step 1: Validate new page with 2 category Content	- Add new page ( AAA) / - Add at least 2 Category Content portlet to new page (AAA) / - Validate AAA by using W3C Validator	No duplicated ID error	Low			hanh.ly	N/A	N/A
008	REG_AIO168_WCM_005	004	REG_AIO168_WCM_005	Validate new page with 2 Content by URL by using W3C Validtor	Step 1: Validate new page with 2 Content by URL	- Add new page ( AAA) / - Add at least 2 Content by URL portlet to new page (AAA) / - Validate AAA by using W3C Validator	No duplicated ID error	Low			hanh.ly	N/A	N/A
009	REG_AIO168_WCM_006	001	REG_AIO168_WCM_006	Check translation of Subscribe in French	Step 1: Check translation	- Login / - Go to ACME/Newsletters / - Input email address and Check to subscribe / - Click on Subscribe / - Change language into French	Button: "ChangeSubscriptions" should be "Modifier mon Abonnement"	High	WCM-2952 / CCP-707	The label of button has no change	hanh.ly	N/A	N/A
010	REG_AIO168_WCM_007	001	REG_AIO168_WCM_007	Check if attribute "target" is in "ACME Overview" when checking with W3C	Step 1: Check Overview page	- Go to ACME Overview / - Validate this page by using W3C validator	Do not throw “there is no attribute "target" “	High	WCM-2939 / CCP-668	There is no attribute X: / Line 2110, column 312: there is no attribute "target" / ...acme/documents/conditions.doc" target="_newdoc">Conditions and Requirements</a...	hanh.ly	N/A	N/A
011	REG_AIO168_WCM_008	001	REG_AIO168_WCM_008	Check Content selector form in IE7	Step 1: Show form to add content	- Login in IE7 / - Select Sites Editor/Add content / - Choose Create new content / - Input title then select Free web layout content / - Click Save	Web content form is shown	High	WCM-2951 / CCP-704		hanh.ly	Passed	Passed
	REG_AIO168_WCM_008	001	REG_AIO168_WCM_008	Check Content selector form in IE7	Step 2: Show form to add content from FCK	In the FCK editor, click Insert Contents icon	Content selector form is shown, the left pane is displayed correctly with all nodes	High	WCM-2951 / CCP-704	this window doesn't contain the left part which shows the tree of acessibles drives/directories: the block is empty	hanh.ly	Passed	Passed
012	REG_AIO168_WCM_009	001	REG_AIO168_WCM_009	Check when creat page link after adding new page for the user navigation	Step 1: Add new page	- Go to SIte Editor --> Add page wizard / - Choose user:root's navigation / - Put values in fields	New page is created successfully	High	WCM-2914 / CCP-588		hanh.ly	Passed	Passed
	REG_AIO168_WCM_009	001	REG_AIO168_WCM_009	Check when creat page link after adding new page for the user navigation	Step 2: Add new document	- Go to Site Explorer -> Site Management / - Select /acme/web content / - Create 1 Free layout webcontent document / - Insert link to the document	Link is inserted into document	High	WCM-2914 / CCP-588	Throw exception	hanh.ly	Passed	Passed
013	REG_AIO168_WCM_010	001	REG_AIO168_WCM_010	Check if labels are translated while adding new page by wizard	Step 1: Check page layout list	- Login / - Change language to French / - Click Site Editor/Add page wizard / - Input valid value for step 1 / - Go to step 2 / - Click on the Page configs to the the Page layout drop down list	The list is well translated in French	High	WCM-2957 / CCP-720		hanh.ly	N/A	N/A
	REG_AIO168_WCM_010	001	REG_AIO168_WCM_010	Check if labels are translated while adding new page by wizard	Step 2: Check translation	- At step 2: select WCM page configs	The list under WCM page configs is shown & well translated in French	High	WCM-2957 / CCP-720		hanh.ly	N/A	N/A
	REG_AIO168_WCM_010	001	REG_AIO168_WCM_010	Check if labels are translated while adding new page by wizard	Step 3: Check translation	- At step 2: select Column page configs	The list under Column page configs is shown & well translated in French	High	WCM-2957 / CCP-720		hanh.ly	N/A	N/A
	REG_AIO168_WCM_010	001	REG_AIO168_WCM_010	Check if labels are translated while adding new page by wizard	Step 4: Check translation	- At step 2: select Row page configs	The list under Row page configs is shown & well translated in French	High	WCM-2957 / CCP-720		hanh.ly	N/A	N/A
	REG_AIO168_WCM_010	001	REG_AIO168_WCM_010	Check if labels are translated while adding new page by wizard	Step 5: Check translation	- At step 2: select Tab page configs	The list under Tab page configs is shown & well translated in French	High	WCM-2957 / CCP-720		hanh.ly	N/A	N/A
	REG_AIO168_WCM_010	001	REG_AIO168_WCM_010	Check if labels are translated while adding new page by wizard	Step 6: Check translation	- At step 2: select Mix page configs	The list under Mix page configs is shown & well translated in French	High	WCM-2957 / CCP-720		hanh.ly	N/A	N/A
014	REG_AIO168_WCM_011	001	REG_AIO168_WCM_011	Check the displaying of exo:link when create CLV by Automatic mode	Step 1: Create a content	- Go to SIte Explorer / - Open form to create new webcontent / - Select template: exo:link (Web link)	Web content is created successfully.	High	WCM-2925 / CCP-639		hanh.ly	Failed	Failed
	REG_AIO168_WCM_011	001	REG_AIO168_WCM_011	Check the displaying of exo:link when create CLV by Automatic mode	Step 2: Check the displaying of exo:link when create CLV by Automatic mode	- Edit CLV page / - Choose Automatic mode / - Open the folder containing that new content	Web link is listed as a document & can be listed in CLV	High	WCM-2925 / CCP-639	Web content appears as a folder.	hanh.ly	Failed	Failed	TESTVN-5426
015	REG_AIO168_WCM_012	001	REG_AIO168_WCM_012	Check displaying of invisible page when creating a portal page link into a text	Step 1: Create invisible page	- Go to SIte Editor --> Add page wizard / - At step 1: do not check in “Visible” check-box	Page is created successfully and it is not displayed in navigation	High	WCM-2960 / CCP-731		hanh.ly	Passed	Passed
	REG_AIO168_WCM_012	001	REG_AIO168_WCM_012	Check displaying of invisible page when creating a portal page link into a text	Step 2: Check displaying of invisible page when creating a portal page link into a text	- Go to Site Explorer / - Open form to create “Free layout web content” / - Click on “Insert link to a site page” icon in FCK / - Click on “Get portal link” button	A window is opened. This page selection window allows to select pages with visible and invisible attribute	High	WCM-2960 / CCP-731	This page selection window allows to select pages with visible attribute but not invisible ones	hanh.ly	Passed	Passed
016	REG_AIO168_WCM_013	001	REG_AIO168_WCM_013	Check displaying .rtf file	Step 1: Open form to upload file	- Login / - Select Site Management drive / - Select /acme/document folder / - Click on “Upload” icon in action bar	“Upload a file” form appears	High	WCM-2943 / CCP-677		hanh.ly	Passed	Passed
	REG_AIO168_WCM_013	001	REG_AIO168_WCM_013	Check displaying .rtf file	Step 2: Upload .rtf file	- Browse 1 .rft file / - Click on Upload icon / - Click on Save button	.rft file is uploaded successful	High	WCM-2943 / CCP-677		hanh.ly	Passed	Passed
	REG_AIO168_WCM_013	001	REG_AIO168_WCM_013	Check displaying .rtf file	Step 3: View content of .rft file	- Select .rft file above	Content of .rft file is not displayed in the right pane. You can download to view its content.	High	WCM-2943 / CCP-677	Error in displaying content.	hanh.ly	Passed	Passed
017	REG_AIO168_WCM_015	001	REG_AIO168_WCM_015	Check if Link can't be distinguished in fck editor edit mode	Step 1: Add SCV	- Edit a page -> insert on it a new scv	SCV is added into page	Low	WCM-2823 / CCP-427		hanh.ly	Passed	Passed
	REG_AIO168_WCM_015	001	REG_AIO168_WCM_015	Check if Link can't be distinguished in fck editor edit mode	Step 2: Add content	- Edit the scv and insert on it a new content, a Free layout WebContent for example. / - In the fck editor of this content, add a link using the insert/edit link icon	The link is displayed as a real link	Low	WCM-2823 / CCP-427	4- The link style will not change(fck_edit_link.JPG). So It couldn't be distinguished from the other content. The problem is not seen in the view mode(fck_view_link.JPG)	hanh.ly	Passed	Passed
018	REG_AIO168_WCM_016	001	REG_AIO168_WCM_016	Check encoding when display Taxonomy in the CLV categories	Step 1: Add new taxonomy tree	- Go to Site administration. / - Go to Ontologies then Manage Taxonomy Trees. / - Click Edit icon at the line of “acme” / - Click Add to add new taxonomy under the acme with name contains accented character like "prévention".	Create new taxonomy tree successfully	High	WCM-2688, WCM-2627, PORTAL-3744 / CCP-302	Currently display error of the header at step 4	hanh.ly	Passed	Passed
	REG_AIO168_WCM_016	001	REG_AIO168_WCM_016	Check encoding when display Taxonomy in the CLV categories	Step 2: Check the displaying the name of new added taxonomy	- Go to the News page in the acme site and click on the category just created	The name of the category is displayed OK in the header	High	WCM-2688, WCM-2627, PORTAL-3744 / CCP-302		hanh.ly	Passed	Passed
019	REG_AIO168_WCM_017	001	REG_AIO168_WCM_017	Check searching with special character while configuring CLV	Step 1: Search with special characters	- Login by root. / - Go to Sites/acme / - Switch edit mode. / - Edit a CLV portlet. / - Choose manual mode. / - Click on the select folder path icon. / - In the content search form, put a text containing * or - / " / - Click Search	Show message alerts There are some invalid characters when search with * and return search result when search with -	Low	WCM-2956 / CCP-713	- Click on the search button. / ==> An error message appears " Unknown error	hanh.ly	Passed	Passed
020	REG_AIO168_WCM_018	001	REG_AIO168_WCM_018	Cache & Categories with publication errors	Step 1: Create web content	- Go to Site Explorer / - Select 1 personal drive (e.g: public) / - Create 1 free layout web content	Create new web content successfully	High	WCM-2725 / CCP-345	Currently at step 8 the change in the web content is not updated (display the old content)	hanh.ly	Passed	Passed
	REG_AIO168_WCM_018	001	REG_AIO168_WCM_018	Cache & Categories with publication errors	Step 2: Edit content	- Select then change content of new added web content	Edit successfully	High	WCM-2725 / CCP-345		hanh.ly	Passed	Passed
	REG_AIO168_WCM_018	001	REG_AIO168_WCM_018	Cache & Categories with publication errors	Step 3: Public node	go to manage publications and choose States and versions based publication: make the node published	Public node successfully	High	WCM-2725 / CCP-345		hanh.ly	Passed	Passed
	REG_AIO168_WCM_018	001	REG_AIO168_WCM_018	Cache & Categories with publication errors	Step 4: Add reference	- Click Manage categories from Action bar / - Select “acme” from Taxonomy Tree / - Choose World, Business, Technology ,Sports	Selected taxonomies are listed in Referenced categories tab	High	WCM-2725 / CCP-345		hanh.ly	Passed	Passed
	REG_AIO168_WCM_018	001	REG_AIO168_WCM_018	Cache & Categories with publication errors	Step 5: View added content	- Choose News page in acme site / - Click World / (do not open other categories)	the node test exist: open it : content 0000 is shown	High	WCM-2725 / CCP-345		hanh.ly	Passed	Passed
	REG_AIO168_WCM_018	001	REG_AIO168_WCM_018	Cache & Categories with publication errors	Step 6: Edit content of web content	- Go to Public drive / - Edit added web content above (change the content)	Change is saved	High	WCM-2725 / CCP-345		hanh.ly	Passed	Passed
	REG_AIO168_WCM_018	001	REG_AIO168_WCM_018	Cache & Categories with publication errors	Step 7: Publish edited content	- Click Manage Publication & Click State	Change is saved	High	WCM-2725 / CCP-345		hanh.ly	Passed	Passed
	REG_AIO168_WCM_018	001	REG_AIO168_WCM_018	Cache & Categories with publication errors	Step 8: Check displaying change of the web content	- Go to News page in acme site & choose World category / - Open the web content from right pane	The web content details is shown with new changes in content (new content is updated in other category)	High	WCM-2725 / CCP-345		hanh.ly	Passed	Passed
021	REG_AIO168_WCM_019	001	REG_AIO168_WCM_019	Check show HTML link in a printed document	Step 1: Create Free layout webcontent	- Go to Site Explorer / - Select 1 personal drive (e.g: public) / - Create 1 free layout web content / - add an HTML link in the document	Create new web content successfully	Low	WCM-2946 / CPP-692		hanh.ly	Passed	Passed
	REG_AIO168_WCM_019	001	REG_AIO168_WCM_019	Check show HTML link in a printed document	Step 2: Public node	go to manage publications and choose States and versions based publication: make the node published	Public node successfully	Low	WCM-2946 / CPP-692		hanh.ly	Passed	Passed
	REG_AIO168_WCM_019	001	REG_AIO168_WCM_019	Check show HTML link in a printed document	Step 3: Add document newly created	- Go to Site Editor/Add content / - Choose the document newly created	The document is selected successfully	Low	WCM-2946 / CPP-692		hanh.ly	Passed	Passed
	REG_AIO168_WCM_019	001	REG_AIO168_WCM_019	Check show HTML link in a printed document	Step 4: show HTML link when printing	- Click Print icon to print this document / Choose to print to a file.	The HTML link is shown in the document	Low	WCM-2946 / CPP-692		hanh.ly	Passed	Passed

## Bugs_v1_6_9
	TEST CASES					Passed	19	19	0	0	0
				Failed	1	1	0	0	0
	Function List:	Bugs fixed WCM 1.2.9 for regression test					Blocked	1	1	0	0	0
	Total Main Cases:	11					Untested	0	0	0	0	0
				N/A	10	10	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
001	REG_AIO169_WCM_001	001	REG_AIO169_WCM_001	Links are displayed not underlined when visited	Step 1: inserting web links	- Go to Sites Explorer/Sites Management/acme/document / - Click add Document / - Choose template for document ( Free layout webcontent)	Free layout web content form appear	High	WCM-2992 / CCP-810		hanh.ly	Passed	Passed
	REG_AIO169_WCM_001	001	REG_AIO169_WCM_001	Links are displayed not underlined when visited	Step 2: Show insert/edit link form	- Click Insert/Edit link on Main content / - Input value for URL and click OK button / - Click on this link	- The link appear underlined / - The link is changed color	High	WCM-2992 / CCP-810		hanh.ly	Passed	Passed
	REG_AIO169_WCM_001	001	REG_AIO169_WCM_001	Links are displayed not underlined when visited	Step 3: inserting portal links	- Go to Sites Explorer/Sites Management/acme/document / - Click add Document / - Choose template for document ( Free layout webcontent)	Free layout web content form appear	High	WCM-2992 / CCP-810		hanh.ly	Passed	Passed
	REG_AIO169_WCM_001	001	REG_AIO169_WCM_001	Links are displayed not underlined when visited	Step 4: Show insert link to a site page form	- Click insert link to a site page form on Main content / - Click Get portal link button / - Select one page in list and Click Save / - Click on this link	- The link appear underlined / - The link is changed color	High	WCM-2992 / CCP-810		hanh.ly	Passed	Passed
	REG_AIO169_WCM_001	001	REG_AIO169_WCM_001	Links are displayed not underlined when visited	Step 5: inserting content	- Go to Sites Explorer/Sites Management/acme/document / - Click add Document / - Choose template for document ( Free layout webcontent)	Free layout web content form appear	High	WCM-2992 / CCP-810		hanh.ly	Passed	Passed
	REG_AIO169_WCM_001	001	REG_AIO169_WCM_001	Links are displayed not underlined when visited	Step 6: Show insert contents form	- Click insert contents on Main content / - In content selector form choose one content / - Click on this link	- The link appear underlined / - The link is changed color	High	WCM-2992 / CCP-810		hanh.ly	Passed	Passed
002	REG_AIO169_WCM_002	001	REG_AIO169_WCM_002	Check if User workspace is closed after edited page using edit page wizard	Step 1: Show edit page wizard	- Login / - Go to Sites Editor/Edit page wizard	Edit page wizard form is shown, User workspace panel is shown on the left	Low	WCM-2959 / CCP-711		hanh.ly	N/A	N/A
	REG_AIO169_WCM_002	001	REG_AIO169_WCM_002	Check if User workspace is closed after edited page using edit page wizard	Step 2: Save changes	- Click Next then Save	Edit page wizard form is closed, User workspace is closed also	Low	WCM-2959 / CCP-711	User workspace is not closed also	hanh.ly	N/A	N/A
003	REG_AIO169_WCM_002	002	REG_AIO169_WCM_002	Check if User workspace is closed after escape edit page wizard	Step 1: Show edit page wizard	- Login / - Go to Sites Editor/Edit page wizard	Edit page wizard form is shown, User workspace panel is shown on the left	Low	WCM-2959 / CCP-711		hanh.ly	N/A	N/A
	REG_AIO169_WCM_002	002	REG_AIO169_WCM_002	Check if User workspace is closed after escape edit page wizard	Step 2: Cancel editing page	Click Abort	Edit page wizard is closed / User workspace is closed also	Low	WCM-2959 / CCP-711	User workspace is not closed also	hanh.ly	N/A	N/A
004	REG_AIO169_WCM_003	003	REG_AIO169_WCM_003	Check if User workspace is closed after edited site	Step 1: Show edit site form	- Login / - Go to Sites Editor/Edit site	Edit current site form is shown / User workspace panel is shown on the left	Low	WCM-2962 / CCP-711		hanh.ly	N/A	N/A
	REG_AIO169_WCM_003	003	REG_AIO169_WCM_003	Check if User workspace is closed after edited site	Step 2: Save changes	- Click Save & Finish icon	Edit current site form is closed / User workspace panel is closed	Low	WCM-2962 / CCP-711	User workspace is not closed also	hanh.ly	N/A	N/A
005	REG_AIO169_WCM_003	004	REG_AIO169_WCM_003	Check if User workspace is closed after escape edit site	Step 1: Show edit site form	- Login / - Go to Sites Editor/Edit site	Edit current site form is shown / User workspace panel is shown on the left	Low	WCM-2962 / CCP-711		hanh.ly	N/A	N/A
	REG_AIO169_WCM_003	004	REG_AIO169_WCM_003	Check if User workspace is closed after escape edit site	Step 2: Quit edit site	Click Discard icon	Edit current site form is closed / User workspace panel is closed	Low	WCM-2962 / CCP-711	User workspace is not closed also	hanh.ly	N/A	N/A
006	REG_AIO169_WCM_004	001	REG_AIO169_WCM_004	Check when download document with apostrophes in name while viewing it form search result	Step 1: Upload file	- Login acme site / - Go to Sites Explorer/Sites Management/acme/document / - Upload a document named: family's	File is uploaded	Low	WCM-2997 / CCP-884		hanh.ly	Passed	Passed
	REG_AIO169_WCM_004	001	REG_AIO169_WCM_004	Check when download document with apostrophes in name while viewing it form search result	Step 2: Publish	- Select uploaded file / - Click Manage Publications / - Choose Live	Document is published	Low	WCM-2997 / CCP-884		hanh.ly	Passed	Passed
	REG_AIO169_WCM_004	001	REG_AIO169_WCM_004	Check when download document with apostrophes in name while viewing it form search result	Step 3: Search	Input search keyword in search text box at the banner & hit enter (that will return uploaded document)	Document is returned in search result	Low	WCM-2997 / CCP-884		hanh.ly	Failed	Failed	TESTVN-5425
	REG_AIO169_WCM_004	001	REG_AIO169_WCM_004	Check when download document with apostrophes in name while viewing it form search result	Step 4: Download	- Click to view document / - Click Download this file link	Form to download file is shown & download successfully	Low	WCM-2997 / CCP-884	Can not dl file	hanh.ly	Blocked	Blocked
007	REG_AIO169_WCM_005	001	REG_AIO169_WCM_005	Check if can change to another page of CLV portlets	Step 1: Add documents	- Login / - Go to Sites Explorer/Sites management/acme/documents / - Add some documents	Documents are added	High	WCM-2944 / CCP-877		hanh.ly	Passed	Passed
	REG_AIO169_WCM_005	001	REG_AIO169_WCM_005	Check if can change to another page of CLV portlets	Step 2: Publish	- Select added document / - Publish	Documents are published	High	WCM-2944 / CCP-877		hanh.ly	Passed	Passed
	REG_AIO169_WCM_005	001	REG_AIO169_WCM_005	Check if can change to another page of CLV portlets	Step 3: View document in FO	- Go to acme Overview page / - In DOCUMENTS part: there's paginator to divide documents list in pages / - Click on the page number to go to other page	- Documents list of selected page No is shown	High	WCM-2944 / CCP-877	a message is shown: "The blockId to update is not found: UICLVPresentation"	hanh.ly	Passed	Passed
008	REG_AIO169_WCM_006	001	REG_AIO169_WCM_006	Check translation in French when viewing documents list	Step 1: Add documents	- Login / - Change language to French / - Go to Sites Explorer/Sites management/acme/documents / - Add some documents	Documents are added	Low	WCM-2968 / CCP-737		hanh.ly	Passed	Passed
	REG_AIO169_WCM_006	001	REG_AIO169_WCM_006	Check translation in French when viewing documents list	Step 2: Public	- Select a document & Publish it	Document is published	Low	WCM-2968 / CCP-737		hanh.ly	Passed	Passed
	REG_AIO169_WCM_006	001	REG_AIO169_WCM_006	Check translation in French when viewing documents list	Step 3: Check documents list	- Select documents folder	Add documents are listed with some informations, all are in French / "published", "draft" should be "publié", "brouillon"	Low	WCM-2968 / CCP-737	"published", "draft" have no change	hanh.ly	N/A	N/A
009	REG_AIO169_WCM_006	002	REG_AIO169_WCM_006	Check translation in French when viewing publish history	Step 1: Add document	- Login / - Change language to French / - Go to Sites Explorer/Sites management/acme/documents / - Add a document	Document is added	Low	WCM-2968 / CCP-737		hanh.ly	Passed	Passed
	REG_AIO169_WCM_006	002	REG_AIO169_WCM_006	Check translation in French when viewing publish history	Step 2: Open publish form	- Select added document / - Click Manage Publication / - Choose History tab	Publish information is shown in French / "published", "draft", "enrolled" should be "publié", "brouillon", "créé"	Low	WCM-2968 / CCP-737		hanh.ly	N/A	N/A
010	REG_AIO169_WCM_007	001	REG_AIO169_WCM_007	Check if can drag container	Step 1: Add page	- Create a new page by wizard / - At step 3: Insert containers on it / Select containers in order to drag them	Drag & drop container successfully	High	WCM-2903 / WCM-2945 / CCP-790	Containers are not dragued	hanh.ly	Passed	Passed
011	REG_AIO169_WCM_008	001	REG_AIO169_WCM_008	Check showing quick edit icon on portlet in porlet mode	Step 1: Add page	- Login as root / - Go to Acme site; create new page AAA / - Add 1 column container to page. Add 1 Content Detail portlet to each container. / - Add 1 other Content Detail portlet outside the column container => then save.	New page is added	High	WCM-2948 / CCP-590		hanh.ly	Passed	Passed
	REG_AIO169_WCM_008	001	REG_AIO169_WCM_008	Check showing quick edit icon on portlet in porlet mode	Step 2: Check Edit icon when resize window	- Go to page AAA and switch to edit mode. / - Resize window	The Edit icon on each portlet is well displayed	High	WCM-2948 / CCP-590	Resize windows => quick edit icon of the portlets in column container disappears.	hanh.ly	Passed	Passed
	REG_AIO169_WCM_008	001	REG_AIO169_WCM_008	Check showing quick edit icon on portlet in porlet mode	Step 3: Check Quick edit icon when move mouse over	Pass mouse over 3 buttons Portlet Mode, Minimize, Maximize (in top-right corner) of the portlets in column container	The Edit icon on each portlet is well displayed	High	WCM-2948 / CCP-590	the quick edit icon of these portlets appears again.	hanh.ly	Passed	Passed
	REG_AIO169_WCM_008	001	REG_AIO169_WCM_008	Check showing quick edit icon on portlet in porlet mode	Step 4: Check Quick edit icon when move mouse over	Pass mouse over 3 buttons Portlet Mode, Minimize, Maximize of the portlets outside column container	The Edit icon on each portlet is well displayed	High	WCM-2948 / CCP-590	the quick edit icon of portlets inside column container disappears.	hanh.ly	Passed	Passed

## Summary_Report
WCM Regression Tests List in AIO				Total cases

Id	Functional Group	Functionality	Functionality Summary
Bugs v.1.6.5
REG_AIO165_WCM_001	WCM	Download	Can not download an uploaded document in PCV portlet	1
REG_AIO165_WCM_002	WCM	Publish	Content edition is not considered after publication	1
REG_AIO165_WCM_004	WCM	Newsletter	Newsletter mail's validator does not REG_WCM_ALLow a multiple domain names in address mail	1
REG_AIO165_WCM_005	WCM	Publish	IE 7 crash when publishing content after image resize with Shift button pressed	1
REG_AIO165_WCM_006	WCM	CLV	Label categories are not traduced in clv edition	1
REG_AIO165_WCM_007	WCM	Localized content	Patch for "Cannot view localised wcm content ( exo:webcontent .... )"	1
REG_AIO165_WCM_008	WCM	Search	Search result - wrong translation of results' number	1
REG_AIO165_WCM_009	WCM	Search	Search result - wrong traduction when there's no result	1
REG_AIO165_WCM_010	WCM	Form Generator	A bad translation of a label in Form Generator Portlet	1
REG_AIO165_WCM_011	WCM	Language	Mistakes in french internationalization	1
REG_AIO165_WCM_012	WCM	Sorting	Problems with Sorting Mechanism	1
REG_AIO165_WCM_014	WCM	WCM	Problem with portlet presentation:StringIndexOutOfBoundsException	1
REG_AIO165_WCM_015	WCM	Manage taxonomy	Problem with manage taxonomy	1
REG_AIO165_WCM_016	WCM	PCLV	Error while setting a page with PCLV portlet	1
REG_AIO165_WCM_017	WCM	PCLV	Problem in downloading binary from PCLV	1
REG_AIO165_WCM_018	WCM	WCM	Problem with "Add a site page link " on FCKEDITOR	1
REG_AIO165_WCM_019	WCM	Publish	Publication problems	1
REG_AIO165_WCM_020	WCM	WCM	WCM Content Selector: does not show content of a folder when switchin	1
REG_AIO165_WCM_021	WCM	WCM	Links in viewMode are not underlined	1
REG_AIO165_WCM_022	WCM	CLV	Error when selecting a content in search result tab of CLV	1
REG_AIO165_WCM_023	WCM	CLV	Inversion of content's list in CLV at every validation	1
REG_AIO165_WCM_024	WCM	FCC	Changes in FCC action's parameters are not taken in consideration	1
REG_AIO165_WCM_025	WCM	Search	Searched texts in search results are not highlighted	1
Bugs v.1.6.6
REG_AIO166_WCM_001	WCM	WCM	A problem with clv when browsing directories with special characters (using IE7)	1
REG_AIO166_WCM_002	WCM	WCM	Problem with displaying documents with name containing illegal JCR characters in PCLV	1
REG_AIO166_WCM_003	WCM	WCM	Can not order content in CLV manual browse	1
REG_AIO166_WCM_004	WCM	WCM	Search's results in FO: Results are not displayed when them number exceeds 250	1
REG_AIO166_WCM_005	WCM	WCM	Labels are not internationalized in WCMInsertContent functionality	1
REG_AIO166_WCM_006	WCM	WCM	Translation of links next and previous in WCM search (FO)	1
REG_AIO166_WCM_007	WCM	WCM	Problem with FCK editor's insert link to a site page plugin	1
REG_AIO166_WCM_008	WCM	WCM	Error when moving document containing illegal jcr characters	1
REG_AIO166_WCM_009	WCM	WCM	the subnodes of nodes that don't have page reference are not shown in the navigation of the WCM site admin toolbar	1
REG_AIO166_WCM_010	WCM	WCM	Impossible to download a binary file with name containing an illegal jcr char (using the right popup menu)	1
REG_AIO166_WCM_011	WCM	WCM	A problem with WCMInsertContent when browsing directories with special characters	1
REG_AIO166_WCM_012	WCM	WCM	Search does not ignore accented characters	1
REG_AIO166_WCM_013	WCM	WCM	Container can't be removed after being inserted in the page	1
REG_AIO166_WCM_014	WCM	WCM	Broken design with empty CLV in manual mode	1
REG_AIO166_WCM_015	WCM	WCM	Show error message when trying to add new category in Newsletter Manager	1
REG_AIO166_WCM_016	WCM	WCM	Problem for displaying documents with names containing illegal JCR characters using nt:file view	1
REG_AIO166_WCM_017	WCM	WCM	Content selector does not work on IE7	1
REG_AIO166_WCM_018	WCM	WCM	Portlet Category Navigation	1
Bugs v.1.6.8
REG_AIO168_WCM_001	WCM	WCM	Portlet Category Navigation	1
REG_AIO168_WCM_002	WCM	WCM	Error while setting a page with PCLV portlet	1
REG_AIO168_WCM_003	WCM	WCM	Link still be referenced after being inserted	1
REG_AIO168_WCM_004	WCM	WCM	Duplicated portlet ID: Content List, Category Navigation, Category Content, Content by URL	1
REG_AIO168_WCM_005	WCM	Newsletter	Newsletter Wrong text of changing "Subscribe" in French	4
REG_AIO168_WCM_006	WCM	WCM	No attribute "target" in "ACME Overview" when checking with W3C	1
REG_AIO168_WCM_007	WCM	WCM	Impossible selection to insert contents into a text content	1
REG_AIO168_WCM_008	WCM	WCM	FCKEditor: Exception when creating page link after adding new page for the user navigation	1
REG_AIO168_WCM_009	WCM	WCM	CLV manual search content: Error when previewing content with image loaded from JCR	1
REG_AIO168_WCM_010	WCM	Language	Add page wizards: Some labels are not translated in French	1
REG_AIO168_WCM_011	WCM	WCM	The selection of repository brings up some content	1
REG_AIO168_WCM_012	WCM	WCM	Impossible to select an invisible page when creating a portal page link into a text (FCK Editor)	1
REG_AIO168_WCM_013	WCM	WCM	Error in displaying .rtf file	1
REG_AIO168_WCM_015	WCM	SCV	Link can't be distinguished in fck editor edit mode	1
REG_AIO168_WCM_016	WCM	CLV	Taxonomy display error in the CLV categories:encoding problem	1
REG_AIO168_WCM_017	WCM	CLV	Error in research when writing characters * and -	1
REG_AIO168_WCM_018	WCM	Publish	Cache & Categories with publication errors	1
Bugs v.1.6.9
REG_AIO169_WCM_001	WCM	WCM	Links are displayed not underlined when visited	1
REG_AIO169_WCM_002	WCM	WCM	The user workspace panel remains visible after editing the current page.	2
REG_AIO169_WCM_003	WCM	WCM	The user workspace panel remains visible after editing the current page.	2
REG_AIO169_WCM_004	WCM	WCM	Bugs when search and download documents which names contain apostrophes.	1
REG_AIO169_WCM_005	WCM	WCM	Check if can change to another page of CLV portlets	1
REG_AIO169_WCM_006	WCM	WCM	Labels aren't translated in French when managing publications	2
REG_AIO169_WCM_007	WCM	WCM	Check if can drag container	1
REG_AIO169_WCM_008	WCM	WCM	Quick edit icons of portlet in column container lost when editing page using IE7	1
Total				72